## Master UC Calendar
| August | September | October | November | December | January | February | March | April | May | June
UC General R2 Communications
User Stories Program WW | bar: November to December
Email - Awareness Target 500
Email - (Target 9k/4k) Welcome to R2
Email - Move confirmation email (4k, 1k)
Email - Client Install (Group A) (2k, 500)
Email - Client Installer (Group B) (2k, 500)
Email - Move confirmation email (5k, 3k)
Email - Client Installer (5k, 3k)
Email - Blocking W12 Client
Email - Move to RC (4k, 2k)
Communicator IM & Presence | bar: January
Training - Self Guided Learning Modules - W12
Training - Self Guided Learning Modules - W13 | bar: November to June
Training - Printed
Training - Videos
Communicator 2007 R2 Getting Started Guide | bar: October to June
Communicator 2007 R2 Quick Reference Card - Conferencing | bar: October to June
Communicator 2007 R2 Quick Reference Card - IM & Presence | bar: October to December
Email - Target 46,509 - LM + EV + VA/C Users
Enterprise Voice | bar: January
Training - Self Guided Learning Modules - W12
Training - Self Guided Learning Modules - W13 | bar: November to June
Training - Printed | bar: August to December
Enterprise Voice User Sat Survey | bar: January to June
Communicator 2007 R2 Quick Reference Card (QRC) - Phone and Video | bar: October to June
Communicator Phone Edition 2007 R2 User Guide | bar: October to June
UC Deskphone R2 New Features Quick Reference Guide | bar: October to December
Email - Target 46,509 - LM + EV + VA/C Users
Dial-in Audio Conferencing | bar: January to June
Training - Print QRG
Training - Videos | bar: October to December
Article - Intranet- A new way to Audio Conference
CA Awareness Campaign deliverables | bar: November to June
Conferencing Auto Attendant Quick Reference Guide | bar: November to June
Dial-In Conferencing Quick Reference Card | bar: November to June
Old way vs. New Way of Conferencing | bar: November to December
Email - Target 46,509 - LM + EV + VA/C Users
Live Meeting/RoundTable
Survey of Existing 1 time users
Email - Target 46,509 - LM + EV + VA/C Users
Email to IT Managers
Review adoption program
FORUM meeting
Understand what IT Managers are doing locally for the Green initiative
Intranet blurbs | bar: January to June
Training - Instructor Led | bar: August to December
Training - LIVE In-Person Road Show | bar: November to June
Training - Self guided Learnng Module 6 | bar: August to December; May to June
Training Self Guided Learning Module for R2 | bar: January to June
Training - print
Training - web | bar: August to December
Conference Room Marketing - WW | bar: October to November
Awarness Campaign - Sticker - WW | bar: October to November
Awarness Campaign - Poster - WW | bar: October to November
Rewards Program -for those who take Mod 6 and increase usage
Chris Caposella Blog
Itweb content | bar: October to June
Live Meeting 2007 Server R2 Getting Started Guide
Live Meeting 2007 Server R2 Quick Reference Card
Communicator Attendant
Training - Printed | bar: October to June
Training - Videos | bar: October to June
Group Chat
Training - Printed
Training - Videos
Group Call/Response Groups
QRG for using Communicator in a Response Group
Communicator Web Access
CWA Getting Started Guide
CWA 2007 R2 Quick Reference Card
This material is provided for your informational purposes only. Microsoft makes no warranties, express or implied. ©2009 Microsoft Corporation.